## Project Overview
Questionnaire
Project Members
Jerin Kavi | Lead
Preethi Angelin
Utkatsh Chandra
Vishwa Shanmuganathan
Project Workflow
S.No | Steps | Owners
1 | Database creation | Preethi Angelin
2 | API | Utkarsh Chandra
3 | Authentication/ | Vishwanath Shanmuganathan
4 | UI
User Story | Date | Story Title | Resource | Status
Q01 | 2025-04-11 | Analysed the project to understand the table requirements | All | Completed
Q02 | 2025-04-11 | Created a rough draft on the tables and the fields required | All | Completed
Q03 | 2025-04-11 | Created the tables Language,Question,Answer | Preethi Angelin | Completed
Q04 | 2025-04-11 | Created the tables Questiontype and QuestionFields | Utkarsh Chandra | Completed
Q05 | 2025-04-11 | Created the tables User and Candidate | Vishwanath Shanmuganathan | Completed
Q06 | 2025-04-11 | Created the tables score and errorviews | Jerin Kavi | Completed
Q07 | 2025-04-11 | Created a migration and created the database and the tables in SSMS | All | Completed
Q08 | 2025-04-11 | Created the PR diagram and sent it for approval | Jerin Kavi | Completed
Q09 | 2025-04-14 | Add answercontroller | Jerin Kavi | Completed
Q10 | 2025-04-14 | Add CandidateController | Preethi Angelin | Completed
Q11 | 2025-04-14 | Add Usercontroller | Utkarsh Chandra | Completed
Q12 | 2025-04-14 | Add Homecontroller | Jerin Kavi | Completed
Q13 | 2025-04-14 | Add LanguageController | Preethi Angelin | Completed
Q14 | 2025-04-15 | Add QuestionController | Utkarsh Chandra | Completed
Q15 | 2025-04-15 | Add QuestionTypeController | Vishwanath Shanmuganathan | Completed
Q16 | 2025-04-15 | Add QuestionFieldController | Jerin Kavi | Completed
Q17 | 2025-04-15 | Add ErrorView Controller | Vishwanath Shanmuganathan | Completed
Q18 | 2025-04-15 | Created DTO and profiler for Candidate table | Jerin Kavi | Completed
Q19 | 2025-04-15 | Created DTO and profiler for Answer table | Preethi Angelin | Completed
Q20 | 2025-04-15 | Created DTO and profiler for Question table | Utkarsh Chandra | In progress
Q21 | 2025-04-15 | Created DTO and profiler for User table | Vishwanath Shanmuganathan | In progress
Q20 | 2025-04-16 | Created DTO and profiler for Question table | Utkarsh Chandra | Completed
Q21 | 2025-04-16 | Created DTO and profiler for User table | Vishwanath Shanmuganathan | Completed
Q22 | 2025-04-16 | Altered the structure of the Database slightly | All | Completed
Q23 | 2025-04-16 | Created serilog for Language table | Vishwanath Shanmuganathan | Completed
Q24 | 2025-04-16 | Created serilog for Candidate table | Vishwanath Shanmuganathan | Completed
Q25 | 2025-04-17 | Done some changes in the Controllers | All | Completed
Q26 | 2025-04-17 | Tested and Corrected the controllers for errors | All | Completed
Q27 | 2025-04-21 | Renamed DTO to entity | Vishwanath Shanmuganathan | Completed
Q28 | 2025-04-21 | Created two way mapping in all the profilers | Jerin Kavi | Completed
Q29 | 2025-04-21 | Created Interface for repository | Preethi Angelin | Completed
Q30 | 2025-04-21 | Created genericRepository Class | Utkarsh Chandra | Completed
Q31 | 2025-04-21 | Implemented Repository pattern into language controller | Jerin Kavi | Completed
Q32 | 2025-04-22 | Did a few changes in profiler | Jerin Kavi | Completed
Q33 | 2025-04-22 | Implemented Repository pattern into QuestionController | All | Completed
Q34 | 2025-04-22 | Tested the CRUD operations in Language Controller | All | Completed
Q35 | 2025-04-22 | Tested the CRUD operations in QuestionController | All | Completed